## Sheet1
This week | Last week | Weeks on list | Risk | Risk resolution progress
3 | - | 1 | Creeping requirements
5 | - | 1 | Requirements gold-plating | Writing a features document which is used as a check for all new requirements. All new features / requirements are put on a list. Items on the list are included or discarded depending on the time available for the product delivery
6 | - | 1 | Released software has low quality
1 | - | 1 | Developer can't provide enough time for project | Going to reserve Monday / Thursday eveings to work on Apollo. Will also plan in Saturday and Sunday evenings when available.
4 | - | 1 | Unfamiliarity with technologies
2 | - | 1 | Incorrect features / requirements | Will post a message on the Rhino forums asking for suggestions. Will also use WIP and beta releases in the early stages to get fast feedback.